## Summary
Testing Start Date-
| SL No | Module Name | Node Name | Description | Status | No Of Bugs Found | No Of Blocker Bugs | No Of Critical Bugs | Major | Minor | Developer's Rating | Developer Name | Tester Name | Remarks
| 1 |  |  |  |  | 8 | 0 | 0 | 7 | 1
| Screen | No. Of Bugs | Open State | Fixed State | Closed State | Deffered | New | NA | Reopen | Product behaviour
|  | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Defect_Log
TITLE | Defect ID | Test Case ID/ Scenario No | Module | Application/ Screen Name | Defect Description | Steps To Reproduce | Severity | Bug Priority | Status | Test type | Date Raised On | Date Closed On | AGE | Tester comments | Developer comments | Remarks / Screen shot of defect | Tester Name | Developer Name | Status | Count | Severity | Count
| 1 |  | Approval | Paysheet Payment | Approver remark is refreshed in 2 nd level approval |  | Minor | Low | Open |  | 2024-12-27 | [5 empty] | Bemina Ravi | Kesava Raja | open | 8 | Blocker | 0
| 2 |  | Approval | Paysheet Payment | Actual amount,Defaulat amount have same value and same currency |  | Major | High | Open |  | 2024-12-27 | [5 empty] | Bemina Ravi | Kesava Raja | Fixed | 0 | Critical | 0
| 3 |  | Approval | Paysheet Payment | PDf is not loading |  | Major | HIgh | Open |  | 2024-12-27 | [5 empty] | Bemina Ravi | Kesava Raja | closed | 0 | Major | 7
| 4 |  | Approval | Paysheet Payment | After rejecting the data is not removed fron desktop-Add approval |  | Major | High | Open |  | 2024-12-27 | [5 empty] | Bemina Ravi | Kesava Raja | New | 0 | Minor | 1
| 5 |  | Approval | Paysheet Payment | After rejecting the data is not removed fron desktop-mod approval |  | Major | High | Open |  | 2024-12-27 | [5 empty] | Bemina Ravi | Kesava Raja | REOPEN | 0 | NA | 0
| 6 |  | Approval | Paysheet Payment | After rejecting the data is not removed fron desktop-cancel approval |  | Major | High | Open |  | 2024-12-27 | [5 empty] | Bemina Ravi | Kesava Raja | Deffered | 0 | Total | 8
| 7 |  | Approval | Paysheet Payment | Old cheque number is loading in approval for mod transaction | In Modify transaction change the cheque number | Major | Medium | Open |  | 2024-12-27 | [7 empty] | NA | 0
| 8 |  | Approval | Paysheet Payment | For Payment taking INR currency |  | Major | High | Open |  | 2024-12-27 | [7 empty] | Product behaviour | 0
[19 empty] | Total | 8

## testcases
Test Case | SNO | Module -Node | Screen Name | Test Case/ Scenario Description | Pre-Condition/Rerequiste | Expected Behavior | Actual Behaviour | Result | Reference ID
TC01
TC02
TC03
TC04
TC05
TC06
TC07
TC08
TC09
TC10
TC11
TC12
TC13
TC14